## Slide 1
Team 54: ECEN215 Lab Kit 2
Bi-Weekly Update 5 Gavin Bernard
Maylun Huang
Evan Slyter
Sponsor: John Lusher TA: Hailey Ward
Notes: Michelle

## Slide 2
Project Summary
Problem statement:
Access to an affordable, course-specific solution for distance-learning students to complete ECEN215 Labs is minimal.
Our Solution:
An affordable, self-contained system that enables hands-on measurements and intuitive data displays.
Complete production of labkit for $50-$75
Easily transportable by hand.
AD3: $379
Notes: Kyle

## Slide 3
Integrated System Diagram
Lab Kit System
User’s Breadboard
BLE
BLE
Notes: Eric

## Slide 4
Project Timeline
2/9 | 2/23 | 3/9 | 3/16 | 3/30 | 4/20
Finalize PCB & order Phone-MCU BLE Validation | Soldered backup PCB Begin App Integration | Solder big PCB | DAC fully integrated | Integrate signal gen Integrate oscilloscope | Final Demo
Notes: Eric

## Slide 5: Power Supply/Signal Generator Gavin Bernard
Accomplishments since last update 18 hrs of effort | Ongoing progress/problems and plans until the next presentation
Validated 5 Volt Buck Converter with 4.988 volts Validated 3.3 Volt Buck Converter with 3.299 volts Validated -5 Volt Charge Pump Inverter with -4.928 volts Validated Variable Voltage Control with 99% accuracy and fixed connective issue with the App Signal Generator operational with frequency and waveform | Fix Signal Generator amplitude Fix connective issue from Micro-USB and ESP32

## Slide 6: Power Supply/Signal Generator Gavin Bernard

## Slide 7: Power Supply/Signal Generator Gavin Bernard

## Slide 8: Power Supply/Signal Generator Gavin Bernard

## Slide 9: Power Supply/Signal Generator Gavin Bernard

## Slide 10: Power Supply/Signal Generator Gavin Bernard

## Slide 11: Power Supply/Signal Generator Gavin Bernard

## Slide 12: Measurement Subsystem Maylun Huang
Accomplishments since last update 14 hrs of effort | Ongoing progress/problems and plans until the next presentation
Validated voltmeter, & single channel oscilloscope In progress validating ohmmeter & dual channel oscilloscope | Fully validate ammeter & second channel of oscilloscope

## Slide 13: Measurement Subsystem Maylun Huang
Voltmeter
Input | Code Reads | Actual
[V] | [V] | [V]
-5 | 0.11 | -5.01 ± 0.07
0 | 1.62 | -0.1 ± 0.1
-5 | 3.23 | 4.98 ± 0.03

## Slide 14: Measurement Subsystem Maylun Huang
Ohmmeter
Component | Raw Input | Actual
[Ω] | [V] | [Ω]
10 | 3 | 10 ± 0.02
100 | 1.65 | 99 ± 0.08
100 | 3 | 102 ± 0.04
1000 | 1.65 | 987 ± 5

## Slide 15: Measurement Subsystem Maylun Huang
Sin Wave, 1V amplitude
100 Hz →
1kHz →

## Slide 16: Mobile App Evan Slyter
Accomplishments since last update 8 hrs of effort | Ongoing progress/problems and plans until the next presentation
-Updated MCU code multiple times to fix reconnection and DAC output issues. -Validated range of app connection -Validated time to send to MCU from app -Validated time to connect to app -Validated connection through obstacles -Validated app-MCU data accuracy | -Integrate Oscilloscope -Integrate Signal Gen -Continue to update code as new problems appear during integration.

## Slide 17: Mobile App Evan Slyter
Trial 1, Flat |  |  |  |  | 
0ft | 2ft | 4ft | 8ft | 10ft | 12ft
+ | + | + | + | - | -
Trial 2, Holding |  |  |  |  | 
0ft | 2ft | 4ft | 8ft | 10ft | 12ft
+ | + | + | + | + | +

## Slide 18: Mobile App Evan Slyter
Trial 1, Flat |  |  |  |  | 
0ft | 2ft | 4ft | 8ft | 10ft | 12ft
0.3s | 0.3s | 5s | 17s | N/A | N/A
Trial 2, Holding |  |  |  |  | 
0ft | 2ft | 4ft | 8ft | 10ft | 12ft
0.3s | 0.3s | 0.3s | 1.5s | 2s | 7s

## Slide 19: Mobile App Evan Slyter

## Slide 20: Mobile App Evan Slyter
Previously failed. Fixed previous issue of command being received by MCU but output not changing.

## Slide 21: Mobile App Evan Slyter
Trial 1 |  |  | 
Case Only | Case + Door | Case + Blanket | Case + Desk
+ | + | + | +
Trial 2, 6ft |  |  | 
Case Only | Case + Door | Case + Blanket | Case + Desk
+ | + | + | +

## Slide 22: Mobile App Evan Slyter
Trial 1, Flat |  |  |  |  | 
0ft | 2ft | 4ft | 8ft | 10ft | 12ft
Instant | Instant | Instant | Instant | 0.3s | 0.3s
Trial 2, Holding |  |  |  |  | 
0ft | 2ft | 4ft | 8ft | 10ft | 12ft
Instant | Instant | Instant | Instant | Instant | Instant

## Slide 23: Execution Plan
Notes: Michelle

## Slide 24: Validation Plan
Notes: Michelle

## Slide 25: Questions?