## Sheet1
Test Name | Success Criteria | Methodology | Status | Owner
Communication Range | Labkit connects to User's device within 8 ft | Connecting device to labkit at 2ft intervals starting with device on top of labkit. | VALIDATED | Evan
Outgoing Communication Time | Labkit sends information to device in <0.5s | A stopwatch will be started at the same time as the Labkit sends data to the phone. Once data is being recieved, the timer will be stopped. | UNTESTED | Evan
Connection Time | Labkit connects to users device within 30 seconds of scanning | A stopwatch will be started as soon as the device begins scanning for a bluetooth connection. Once the scan finds the Labkit and the Labkit succesfully connects, the timer will be stopped | VALIDATED | Evan
Communication Accuracy | Binary data recieved on Labkit is the same data sent from User's device | Data is sent from the User's device to the labkit. We will ensure we know which sequence is being sent and check what arrives at the MCU. | VALIDATED | Evan
Communication Strength | Labkit connects to User's device through minor obstacles. | Connecting the device to the labkit when the labkit is covered by a blanket, under a desk, and behind a door. | VALIDATED | Evan
Incoming Communication Time | Labkit recieves information from device in <0.75s | A stopwatch will be started at the same time as the phone sends a command to the Labkit. Once the command is received and completed, the timer will be stopped. | VALIDATED | Evan
Power supplies correct voltage following command from app | Power supply sucessfully sets output voltage to whatever is said by binary data. | Once binary accuracy is confirmed, see if MCU code reads it correctly and sets output voltage as expected for voltages of 0,0.5,3.3, and 5. | VALIDATED | Evan + Gavin
Signal Generator can be controlled by the App | Signal Generator successfully changes the frequency,waveform, and voltage to whatever is inputted from the app. | Input from the app using code that was developed prior and then test using an oscilliscope if the output is correct to the expected input. | PARTIALLY VALIDATED | Evan + Gavin
Multimeter Voltage Testing | Measures -5 to 5V within 2% accuracy | Use bench multimeter to measure scaled voltage measurements, and compare to ideal measurements, then decode using MCU code | VALIDATED | Maylun
Multimeter Current Testing | Measures 0 to 1A within 2% accuracy | Use bench multimeter to measure scaled voltage measurements, and compare to ideal measurements, then decode using MCU code | VALIDATED | Maylun
Multimeter Resistance Testing | Measures 10 to 10kΩ within 2% accuracy | Use bench multimeter to measure scaled voltage measurements, and compare to ideal measurements, then decode using MCU code | VALIDATED | Maylun
Oscilloscope | Graph signals up to 10kHz | Use bench oscilloscope to graph outputted signal, and use MCU to graph output for single and dual channel | VALIDATED | Maylun
LabKit Measurements | LabKit receives and formats measurements | Apply multimeter and oscilloscope, and view output on Mobile App | PARTIALLY VALIDATED | Maylun
LabKit 5 Volt Output | LabKit is able to output 5 Volts and 1 Amps | 12 Volt and 5 amp input uses a buck converter to step down the voltage and current to 5 volts and 1 amps | VALIDATED | Gavin
LabKit 3.3 Volt Output | LabKit is able to output 3.3 Volts and 1 Amp | Takes input and steps down the voltage to 3.3 volts and 1 amp to help power the ESP32 and other components within the system | VALIDATED | Gavin
LabKit Controllable Variable Voltage | LabKit is able to control a variable voltage output from 0 to 5 Volts | Uses a digital-to-analog converter that is connected to the ESP 32 that allows for a controllable output voltage that can be used for different aspects in the circuits | VALIDATED | Gavin
LabKit -5 Volt Output | LabKit is able to output -5 Volts with 40 mA | Uses an inverter to change the 5 volt input to -5 volts so students can operate op amps | VALIDATED | Gavin
Sine, Ramp, and Square Signal Generator | Able to generate a Sine, Ramp, and Square Signal | Signal generator is connected to the ESP 32 that allows for a controllable waveform | PARTIALLY VALIDATED | Gavin
Signal Generation | Able to output a signal that can be measured | A waveform is able to be outputted and connected to a circuit for students to measure | VALIDATED | Gavin
20 - 1,500 Hz Frequency Change | Able to change the signal frequency in the range of 20 Hz to 1,500 Hz | With the Signal generator connected to the ESP 32, it can also change the frequency within the range expressed | PARTIALLY VALIDATED | Gavin
DC Power Supply Current Load | Able to power the entire product and power every lab needed. | While fully integrated, able to support every lab with enough current for students to take measurements. | VALIDATED | Gavin
System Reset Time | Labkit becomes availble to connect to users device within 30 seconds of being powered | A stopwatch will be started as the Labkit is connected to power. The stopwatch will be stopped once the Labkit is detected by the user's device | VALIDATED | Evan
0.5 - 2.0 V Op Amp Controllable Output | Able to control the signal voltage from 0.5 Volts to 2 Volts | External op amp connected to a digital potentiometer can be regulated by the ESP 32 to help change the voltage of the signal created | PARTIALLY VALIDATED | Gavin
UNTESTED
UNTESTED
UNTESTED
UNTESTED
UNTESTED
UNTESTED
UNTESTED
UNTESTED